## Project Plan
Blockchain-Based Digital Contract Verification System
Project Management Plan · Field Details
§ | Field | Details
I. Project Overview
I | Project Title | Blockchain-Based Digital Contract Verification System
| Project Aim | Ensuring document integrity via SHA-256 digital fingerprinting.
| Core Concept | Simulating blockchain hash-chain logic for PDF contracts.
II. Team & Roles
II | Project Manager | Özge Zelal Küçük — Jira Management, Sprint Planning & Timeline Coordination
| System Analyst | Kevser Agdas — UML Design (Use Case, Class & Sequence Diagrams)
| Backend Developer | Muhammed Dönmez — SHA-256 Hashing Logic, Flask API & Blockchain Simulation
| Frontend Developer | Sude Özübek — UI Design, File Upload Interface & API Integration
| QA & DevOps | Yağmur Saraçoğlu — GitHub Management, Pytest Testing & Documentation
III. Timeline (12-Week Project Plan)
III | Week 1 | Project Initiation — Jira setup, GitHub repo creation, role assignments, tool installation
| Week 2 | Requirements Analysis — Functional & non-functional requirements, UML Use Case & Class diagrams
| Week 3 | Database Design — SQLite schema (users, contracts, blocks tables), ER diagram, SQLAlchemy models
| Week 4 | Backend: Auth — User register/login endpoints, JWT token authentication, password hashing
| Week 5 | Backend: Blockchain — SHA-256 hash engine, Block class, Blockchain chain simulation, unit tests
| Week 6 | Backend: File API — PDF upload endpoint, hash generation on upload, block stored in DB
| Week 7 | Frontend: Core UI — Login/Register pages, Dashboard, PDF upload form (drag & drop)
| Week 8 | System Integration — Connect frontend to backend API, CORS setup, error handling
| Week 9 | Quality Testing & Bug Fixing — Pytest test cases, Postman API tests, tamper-detection tests
| Week 10 | Audit Log & Dashboard — Verification history table, filter by user/date, admin view
| Week 11 | Final Documentation — Project report, API docs, UML updates, GitHub README
| Week 12 | Submission — Final GitHub push, tag release v1.0, share link with teacher on UBIS
IV. Budget
IV | Human Resources | 5 Software Engineers · ~25 hrs/week each · 480 Total Man-Hours (12 Weeks)
| Software Tools | Jira Cloud (Free), GitHub (Free), draw.io, PlantUML, Python hashlib, Flask, Bootstrap 5
| Hardware | 5 Development Laptops (Existing Personal Resources — no additional cost)
| Total Cost | $0 (Resource-based Simulation — all tools are free / open-source)

## Timeline Gantt
Timeline Gantt — 12-Week Sprint Overview
# | Task / Phase | Responsible | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
1 | Project Initiation & Jira Setup | Project Manager | [12 empty] | Sprint 1 | bar: W1
2 | Requirements & UML Diagrams | System Analyst
3 | GitHub Repo & DevOps Setup | QA & DevOps | bar: W1 to W2
4 | DB Design & SQLAlchemy Models | QA & DevOps | [12 empty] | Sprint 2
5 | Backend: Auth (Register/Login/JWT) | Backend Developer | bar: W4
6 | Backend: SHA-256 & Blockchain Class | Backend Developer
7 | Backend: Upload & Verify API | Backend Developer | [12 empty] | Sprint 3 | bar: W6
8 | Frontend: Login/Dashboard/Upload UI | Frontend Developer
9 | System Integration (API ↔ UI) | All Members | bar: W8
10 | Testing & Bug Fixing | QA & DevOps | [12 empty] | Sprint 4
11 | Audit Log & History Dashboard | Frontend Developer | bar: W10
12 | Documentation & Project Report | System Analyst
13 | Final Submission & GitHub Release | Project Manager | bar: W12

## Budget Details
Budget Planning — Resource Breakdown
Human Resources
Role | Member | Hrs/Week | Total (12 Wks)
Project Manager | Özge Zelal Küçük | 10 | 120
System Analyst | Kevser Agdas | 10 | 120
Backend Developer | Muhammed Dönmez | 10 | 120
Frontend Developer | Sude Özübek | 10 | 120
QA & DevOps | Yağmur Saraçoğlu | 10 | 120
TOTAL MAN-HOURS (12 Weeks) |  |  | 600
Software & Hardware Resources
Resource | Purpose | License | Cost
Jira Cloud (Free) | Sprint & task management | Free ≤10 users | $0
GitHub (Free) | Version control & repository | Free (public) | $0
draw.io | UML diagrams | Free (online) | $0
PlantUML | Code-based UML diagrams | Open Source | $0
Python 3.11 | Core backend language | Open Source | $0
Flask | Web API framework | Open Source | $0
hashlib (SHA-256) | Cryptographic hash engine | Built-in | $0
SQLite | Database engine | Built-in | $0
Bootstrap 5 | Frontend UI framework | Open Source | $0
pytest | Automated testing | Open Source | $0
5× Dev Laptops | Existing personal hardware | Owned | $0
TOTAL PROJECT COST |  |  | $0 (Resource-based Simulation)